## Dashboard
MEETING AUDIO -> NOTES, ACTIONS, SRT
Independent demo - synthetic audio - human-corrected transcript used for final notes
Meetings | 3 | Audio duration | 4:21
Action items | 13 | Decisions | 3
Risks | 3 | Average raw ASR WER | 19.5%
What the client receives |  | Raw ASR vs final notes
✓ | Meeting summaries | Raw transcript | 19.5% WER
✓ | Key points | Final notes | Human-corrected
✓ | Decisions and risks | Captions | 25 segments
✓ | Action items with owners and due dates
✓ | English / Chinese / bilingual SRT
✓ | Excel workbook + source script

## Meetings
id | title | date | duration_seconds | participants | action_count | decision_count | risk_count | key_point_count | average_wer
meeting-01 | Weekly Product Sync | 2026-10-12 | 102.6 | Ava, Noah, Mia, Liam, Emma | 5 | 1 | 1 | 2 | 0.2022
meeting-02 | Client Onboarding Call | 2026-10-14 | 78.8 | Liam, Emma, Lucas, Ava | 4 | 1 | 1 | 1 | 0.2074
meeting-03 | Operations Review | 2026-10-16 | 80.5 | Lucas, Ava, Noah, Mia | 4 | 1 | 1 | 1 | 0.1765

## Action Items
meeting_id | meeting_title | meeting_date | owner | speaker | task | due_date | due_phrase | source_sentence
meeting-01 | Weekly Product Sync | 2026-10-12 | Noah | Noah | update the pricing sheet | 2026-10-14 | by Wednesday | I checked the pricing sheet yesterday. The annual plan is missing two regional prices. Action item: Noah will update the pricing sheet by Wednesday.
meeting-01 | Weekly Product Sync | 2026-10-12 | Liam | Liam | send the revised launch deck | 2026-10-16 | by Friday | The revised launch deck is ready for review. Action item: Liam will send the revised launch deck by Friday.
meeting-01 | Weekly Product Sync | 2026-10-12 | Emma | Emma | book the customer interview | 2026-10-20 | for next Tuesday | I can book the customer interview. Action item: Emma will book the customer interview for next Tuesday.
meeting-01 | Weekly Product Sync | 2026-10-12 | Noah | Noah | prepare the fallback pricing option | 2026-10-19 | by Monday | I will prepare a fallback pricing option. Action item: Noah will prepare the fallback pricing option by Monday.
meeting-01 | Weekly Product Sync | 2026-10-12 | Mia | Mia | draft the onboarding checklist | 2026-10-15 | by Thursday | I will draft the new onboarding checklist. Action item: Mia will draft the onboarding checklist by Thursday.
meeting-02 | Client Onboarding Call | 2026-10-14 | Emma | Emma | send the onboarding checklist | 2026-10-15 | by tomorrow | I will send the onboarding checklist today. Action item: Emma will send the onboarding checklist by tomorrow.
meeting-02 | Client Onboarding Call | 2026-10-14 | Liam | Liam | schedule the kickoff | 2026-10-28 | for October 28 | I will schedule the kickoff. Action item: Liam will schedule the kickoff for October 28.
meeting-02 | Client Onboarding Call | 2026-10-14 | Emma | Emma | prepare the training video | 2026-10-21 | by next Wednesday | I will prepare a short training video. Action item: Emma will prepare the training video by next Wednesday.
meeting-02 | Client Onboarding Call | 2026-10-14 | Lucas | Lucas | clean the sample data | 2026-10-19 | by Monday | I will clean the sample data before the kickoff. Action item: Lucas will clean the sample data by Monday.
meeting-03 | Operations Review | 2026-10-16 | Ava | Ava | review the exception log | 2026-10-22 | by Thursday | I reviewed the exception log. Most errors come from missing PO numbers and duplicate invoices. Action item: Ava will review the exception log by Thursday.
meeting-03 | Operations Review | 2026-10-16 | Noah | Noah | prepare the weekly dashboard | 2026-10-19 | by Monday | I will prepare the weekly dashboard. Action item: Noah will prepare the weekly dashboard by Monday.
meeting-03 | Operations Review | 2026-10-16 | Ava | Ava | ask finance for approval | 2026-10-21 | by Wednesday | I will ask finance for approval. Action item: Ava will ask finance for approval by Wednesday.
meeting-03 | Operations Review | 2026-10-16 | Mia | Mia | update the operations guide | 2026-10-23 | by Friday | I will update the operations guide. Action item: Mia will update the operations guide by Friday.

## Decisions
meeting_id | meeting_title | meeting_date | decision | source_sentence
meeting-01 | Weekly Product Sync | 2026-10-12 | we will delay the public beta by one week to finish the payment integration. | Decision: we will delay the public beta by one week to finish the payment integration. Risk: the vendor may miss the new deadline, so we need a fallback plan.
meeting-02 | Client Onboarding Call | 2026-10-14 | we will start with a pilot of two teams instead of the full company. | Decision: we will start with a pilot of two teams instead of the full company.
meeting-03 | Operations Review | 2026-10-16 | we will move the invoice process to the new template starting next month. | The new invoice template is ready. Decision: we will move the invoice process to the new template starting next month.

## Risks
meeting_id | meeting_title | meeting_date | risk | source_sentence
meeting-01 | Weekly Product Sync | 2026-10-12 | the vendor may miss the new deadline, so we need a fallback plan. | Decision: we will delay the public beta by one week to finish the payment integration. Risk: the vendor may miss the new deadline, so we need a fallback plan.
meeting-02 | Client Onboarding Call | 2026-10-14 | the missing fields may delay the import. | The client's data export has three missing fields. Risk: the missing fields may delay the import.
meeting-03 | Operations Review | 2026-10-16 | the finance team has not approved the new template yet. | Risk: the finance team has not approved the new template yet.

## Key Points
meeting_id | meeting_title | meeting_date | key_point | source_sentence
meeting-01 | Weekly Product Sync | 2026-10-12 | the beta launch is still on track for October 30, but the payment integration is blocked by the vendor. | Good morning. Let's review the launch plan. Key point: the beta launch is still on track for October 30, but the payment integration is blocked by the vendor.
meeting-01 | Weekly Product Sync | 2026-10-12 | onboarding is the top usability concern. | I spoke with three beta customers. They want a simpler onboarding flow. Key point: onboarding is the top usability concern.
meeting-02 | Client Onboarding Call | 2026-10-14 | the initial rollout will cover the US only. | Welcome. The client wants to start with the US region and add Europe later. Key point: the initial rollout will cover the US only.
meeting-03 | Operations Review | 2026-10-16 | the manual cleanup is the biggest bottleneck. | The weekly report still takes four hours to prepare. Key point: the manual cleanup is the biggest bottleneck.

## Transcript Segments
meeting_id | speaker | start | end | en | zh
meeting-01 | Ava | 6.21 | 17.97 | Good morning. Let's review the launch plan. Key point: the beta launch is still on track for October 30, but the payment integration is blocked by the vendor. | 早上好。我们来回顾发布计划。关键点：Beta 发布仍按计划在 10 月 30 日进行，但支付集成被供应商阻塞。
meeting-01 | Noah | 20.22 | 30.96 | I checked the pricing sheet yesterday. The annual plan is missing two regional prices. Action item: Noah will update the pricing sheet by Wednesday. | 我昨天检查了价格表。年度计划缺少两个区域价格。行动项：Noah 将在周三前更新价格表。
meeting-01 | Mia | 33.21 | 42.75 | I spoke with three beta customers. They want a simpler onboarding flow. Key point: onboarding is the top usability concern. | 我和三位 Beta 客户沟通过了。他们希望有更简单的入驻流程。关键点：入驻流程是最大的可用性问题。
meeting-01 | Liam | 45.18 | 52.68 | The revised launch deck is ready for review. Action item: Liam will send the revised launch deck by Friday. | 修订后的发布演示文稿已经可以审阅。行动项：Liam 将在周五前发送修订后的发布演示文稿。
meeting-01 | Emma | 54.96 | 61.98 | I can book the customer interview. Action item: Emma will book the customer interview for next Tuesday. | 我可以预约客户访谈。行动项：Emma 将在下周二预约客户访谈。
meeting-01 | Ava | 64.23 | 75.39 | Decision: we will delay the public beta by one week to finish the payment integration. Risk: the vendor may miss the new deadline, so we need a fallback plan. | 决定：我们将公开 Beta 推迟一周，以完成支付集成。风险：供应商可能错过新的截止日期，所以我们需要一个备用方案。
meeting-01 | Noah | 77.67 | 85.47 | I will prepare a fallback pricing option. Action item: Noah will prepare the fallback pricing option by Monday. | 我会准备一个备用定价方案。行动项：Noah 将在周一前准备备用定价方案。
meeting-01 | Mia | 87.72 | 95.13 | I will draft the new onboarding checklist. Action item: Mia will draft the onboarding checklist by Thursday. | 我会起草新的入驻检查清单。行动项：Mia 将在周四前起草入驻检查清单。
meeting-01 | Ava | 97.38 | 101.76 | Great. We will review progress in the next sync on Friday. | 很好。我们将在周五的下一次同步会上回顾进展。
meeting-02 | Liam | 6.51 | 16.53 | Welcome. The client wants to start with the US region and add Europe later. Key point: the initial rollout will cover the US only. | 欢迎。客户希望先在美国区域开始，之后再扩展到欧洲。关键点：初始上线只覆盖美国。
meeting-02 | Emma | 18.78 | 26.1 | I will send the onboarding checklist today. Action item: Emma will send the onboarding checklist by tomorrow. | 我今天会发送入驻检查清单。行动项：Emma 将在明天前发送入驻检查清单。
meeting-02 | Lucas | 28.62 | 35.73 | The client's data export has three missing fields. Risk: the missing fields may delay the import. | 客户的数据导出缺少三个字段。风险：缺失字段可能会延迟导入。
meeting-02 | Ava | 38.01 | 42.72 | Decision: we will start with a pilot of two teams instead of the full company. | 决定：我们将先以两个团队进行试点，而不是全公司上线。
meeting-02 | Liam | 45.12 | 54.24 | I will schedule the kickoff. Action item: Liam will schedule the kickoff for October 28. | 我会安排启动会。行动项：Liam 将在 10 月 28 日安排启动会。
meeting-02 | Emma | 54.39 | 61.62 | I will prepare a short training video. Action item: Emma will prepare the training video by next Wednesday. | 我会准备一个简短的培训视频。行动项：Emma 将在下周三前准备培训视频。
meeting-02 | Lucas | 64.11 | 71.43 | I will clean the sample data before the kickoff. Action item: Lucas will clean the sample data by Monday. | 我会在启动会前清理示例数据。行动项：Lucas 将在周一前清理示例数据。
meeting-02 | Ava | 73.68 | 77.97 | Good. We will confirm the pilot scope in the kickoff call. | 很好。我们将在启动会上确认试点范围。
meeting-03 | Lucas | 6.48 | 14.25 | The weekly report still takes four hours to prepare. Key point: the manual cleanup is the biggest bottleneck. | 周报仍然需要四个小时来准备。关键点：手工清理是最大的瓶颈。
meeting-03 | Ava | 16.56 | 27.81 | I reviewed the exception log. Most errors come from missing PO numbers and duplicate invoices. Action item: Ava will review the exception log by Thursday. | 我审阅了异常日志。大多数错误来自缺少采购订单号和重复发票。行动项：Ava 将在周四前审阅异常日志。
meeting-03 | Noah | 30.06 | 36.93 | I will prepare the weekly dashboard. Action item: Noah will prepare the weekly dashboard by Monday. | 我会准备周报仪表盘。行动项：Noah 将在周一前准备周报仪表盘。
meeting-03 | Mia | 39.18 | 46.8 | The new invoice template is ready. Decision: we will move the invoice process to the new template starting next month. | 新的发票模板已经准备好了。决定：我们将从下个月开始把发票流程迁移到新模板。
meeting-03 | Lucas | 49.35 | 53.37 | Risk: the finance team has not approved the new template yet. | 风险：财务团队还没有批准新模板。
meeting-03 | Ava | 55.68 | 62.58 | I will ask finance for approval. Action item: Ava will ask finance for approval by Wednesday. | 我会向财务申请批准。行动项：Ava 将在周三前向财务申请批准。
meeting-03 | Mia | 64.83 | 71.94 | I will update the operations guide. Action item: Mia will update the operations guide by Friday. | 我会更新运营指南。行动项：Mia 将在周五前更新运营指南。
meeting-03 | Lucas | 74.46 | 79.74 | Good. We will review the first month of results in the next operations review. | 很好。我们将在下一次运营回顾会上审阅第一个月的结果。

## Owner Summary
owner | action_count
Noah | 3
Emma | 3
Liam | 2
Mia | 2
Ava | 2
Lucas | 1